## Slide 1: Pharmacovigilance Projects Project Management Concerns
August 2023

## Slide 2: Lessons Learned
Our approach is based on Agile Scrum, but in our Lessons Learned, we identified that we are not adhering to all of the Scrum ceremonies, like Sprint Reviews and Retros.
We are using GitLab, which has brought some frustrations… is that us or the tool?
Perhaps Kanban is a more appropriate approach? Kanban is a workflow management method that organizes and improves systems of work. It originated with Toyota in the late 1940s as a scheduling system for just-in-time manufacturing. Kanban helps us visualize work in progress, maximize efficiency, and improve continuously, by representing the state of every piece of work on a single board that team members can refer to at any time.
Kanban is quite like what we are currently trying to do.
What we are currently doing is more like Kanban than Scrum, but Kanban is also looser.

## Slide 3: Agile Ceremonies
Agile ceremonies are meetings held on a regular basis with the goal of building an information flow of internal or external feedback within a team or the entire organization. They are an integral part of every Agile project.
Sprint Planning: A meeting where the development team, scrum master, and product owner plan what work will be completed during the upcoming sprint. The team identifies the sprint goal, backlog, and tasks needed to deliver the sprint increment.
Daily Stand-Up: A short, time-boxed meeting where the development team shares their progress, challenges, and plans for the day.
  What did I do yesterday?
  What will I do today?
  Is anything blocking me?
Sprint Review: A meeting where the development team demonstrates the work done during the sprint to the product owner and other stakeholders. The team receives feedback and validates whether the sprint goal was met.
Sprint Retrospective: A meeting where the development team, the scrum master, and the product owner reflect on how the sprint went and identify areas for improvement.
Sprint Planning
Stand-Up
Sprint Review
Retro
Could we surface more often?
How is the team feeling?
What is our sprint goal?

## Slide 4: Kanban 101
Key Characteristics of Kanban
Workflow transparency: Kanban uses a board to show the different stages of work and the status of each work item. This helps team members and stakeholders see the flow of work and identify any bottlenecks or blockers.
Focus on completing instead of starting work: Kanban limits the amount of work in progress (WIP) in each stage to prevent multitasking and context switching. This helps team members concentrate on finishing their current tasks before starting new ones.
Flow efficiency: Kanban aims to optimize the time that work items spend in value-adding activities rather than waiting or being transferred. This helps reduce lead time and increase customer satisfaction.
Respect for current roles and processes: Kanban does not prescribe any specific roles or processes for teams. Instead, it respects the existing ones and encourages teams to experiment and improve them gradually.
WIP
Flow
Respect
Efficiency

## Slide 5: Kanban 101
Kanban is not:
Based on Sprints: Kanban does not use a sprint backlog, because it does not have sprints or time-boxes. Kanban uses a kanban board to visualize and manage the flow of work from the product backlog to completion.
Based on Story Points: Story points are a way of estimating issues in Scrum, but they are not effective or required in Kanban. Kanban prioritizes flow over velocity.
A Process Framework: Kanban does not prescribe specific roles, ceremonies, artifacts, or rules. It is a management method that should be applied to an existing process.
A Software Delivery Lifecycle: Kanban does not define any phases or stages of work (planning, design, development, testing, deployment). Instead, Kanban focuses on managing the flow of work from backlog to completion.
Standalone: Kanban can be used in combination with other methods or frameworks, such as Scrum, Lean, Agile, or Just-in-Time (JIT). Kanban enhances efficiency of these systems using boards, cards, columns and limits.
Boards
Cards
Columns
Limits
Milestones
Issue Boards
Issues
Incidents
Unstarted, Ongoing, Completed
Lists and Labels
Charts are Premium
Count cards in a column
GitLab has support for:
GitLab gives us a board and transparency, but we need to keep it simple and uncluttered.

## Slide 6: Proposed Development Milestone Flow
TO DO
In a GitLab Milestone:
Unstarted Issues
Backlog: there should be a healthy number of issues here until we reach Milestone completion.
DOING
In a GitLab Milestone:
Assigned Issues
Work in Progress: should never be more than around 5-10 Issues here. Large quantities of WIP indicate a bottleneck.
Labels/Lists Ready For Testing Analysis Required Decision Required
DONE
In a GitLab Milestone:
Completed Issues
Completed Work: should increase over time in a more or less linear way.
Questions:
Do we create one Milestone per release, or do we keep using Sprints, but consider a longer increment?
How long should a Milestone be if not broken up into increments? 3 mths?
Will this work for Requirements as well as developed changes?
If we stop using sprints, we still do daily scrums and weekly backlog grooming.
Push to Production after a successful demo of new product features?

## Slide 7: A Separate Milestone for Production
TO DO
In a GitLab Milestone:
Unstarted Issues
Backlog: This represents our planned future work (releases).
DOING
In a GitLab Milestone:
Ongoing Issues
Work in Progress: There should be a single Issue here, representing our current WIP, and no more than a handful of Incidents .
DONE
In a GitLab Milestone:
Completed Issues
Completed Work: should increase over time in a more or less linear way as we remediate and improve PROD.
Production Release Notes and Incidents
When something breaks, we can create an Incident, develop a hot-fix, move the Incident quickly from DOING to DONE.
For planned releases, we can create an Issue to represent the release, including release notes indicating Issues resolved.
We currently have a Released label, but why not just close completed releases?

## Slide 8: A Separate Milestone for Backlog (?)
We probably don’t need this…
  We can create a board showing all unassigned Issues and select which of those to move into an open Milestone/Iteration/Sprint.
  We can look at an open Milestone and see all of the Unstarted, Ongoing, and Completed Issues.
  There should also be no need to assign a Product Backlog label. This just creates work when, by definition, any new Issues should be in our backlog.
Recommendation:
  Add a “--- Ready ---” Issue to our main Issue Board
  Unassign all Product Backlog Issues, returning them to the Unstarted column
  Move Product Backlog Issues that are “ready” above the line

## Slide 9: Main Issue Board
Unassigned
Unstarted Issues
Analysis Required
Assigned Issues
Decision Required
Delayed Issues
These work items are not ready for development and require a business decision: not WIP.
Closed
Developed Issues
Ready For Review
Completed Issues
Completed Work:
This should increase over time in linear fashion as we remediate and improve PROD
Product Backlog:
This represents our potential for future work.
We should use a “ready” line to indicate work that is ready to move into development.
These work items are not ready for development and require further analysis: Possibly WIP?
Open
Assigned Issues
Work in Progress:
This represents the features and issues currently in development.
There should not be more than 5-10 Issues here. Excess WIP indicates a bottleneck.
Work in Progress:
This represents work that needs to be reviewed by the product owner and then either closed or moved back into a previous state.